## Sheet1
Project Title: | SKM FIBC
Enquiry Date: | 2017-06-30
Enquiry: | Need a control panel with plc logic to automate their machanical FIBC bag filling machine.
Background Info: | Bulk filling is done manually by operator. Operator has to present at the filling spot and keep their eyes on the weighing scale- once the bag reaches a certain weight, the operator has to either press the stop button or trigger a slowdown.
Requirements: | * Control panel
* Siemens PLC ladder logic
* Siemens HMI interface design for status monitoring
* Provide all sensors
* Sensor installation and termination
* Wiring and piping
* Infinite box iot (optional add on)
Proposed solution: | Gather information and identify all the sensor required
Fabricate the panel and internal wiring
Siemens PLC ladder logic programming
Siemens HMI design and connection with PLC
Wiring piping and termination
Materials list- Cost: |  | Units | Unit Cost | Calculated Cost
| Contactor & Overload relay | 3
| Relay | 6
| Circuit Breaker (3 Phase) | 1
| 24VDC Power Supply | 1
| Terminal block | 4
| 24VDC Wire | 2
| 24VDC Tower Light | 1
| Wire Lugs (3mm) | 2
| Wire Lugs (5mm) | 1
| External Power Switch | 1
| Green Button | 1
| Red Button | 1
| Red Light | 2
| Green Light | 1
| Yellow Light | 1
| Blue Light | 1
| EMO | 2
| RYB Wires | 1
| Solenoid Valve | 4
| Prox Sensor (Knife gate) | 3
| Prox Sensor (Clamp) | 2
| Prox Sensor (Hoist) | 4
| Limit Switch (Diverter) | 2
| Load Cell | 2
| Main Control Panel | 1
| Junction Box (Main Termination Point) | 1
| PLC Siemens | 1
| HMI Siemens | 1
Block Diagram:
Machine Op Logic:
|  |  | Start Date | Est Completion Date | Actual Completion Date
ip66 panel
Required Action | Identify Components Model & Specs | Victor | 2017-07-05 | 2017-07-07
| Purchase of all required materials | Victor | 2017-07-05 | 2017-07-12
| Recommend a suitable sensor to BAFE | Victor | 2017-07-08 | 2017-07-12
| Control panel standard wiring | Victor | 2017-07-12 | 2017-07-15
| Siemens PLC ladder logic completion | Victor | 2017-07-10 | 2017-07-22
| Completion of panel wiring including 24vdc circuit | Victor | 2017-07-10 | 2017-07-29
| Siemens HMI Completion | Victor | 2017-07-20 | 2017-07-31
| Wirings of external sensors of mechanical parts | Victor & Vasu | 2017-07-20 | 2017-07-31

## IO List
Inputs | Tag | Address | Remarks | Output | Tag | Address | Remarks | Parts
Knife Gate | KGI1 | I-0 | Opened | Knife Gate | KGO1 | O-1 | Opening | 24V Relay - S Valve
Knife Gate | KGI2 | I-1 | Mid | Knife Gate | KGO2 | O-2 | Closing | 24V Relay - S Valve
Knife Gate | KGI3 | I-2 | Closed | Clamp | CLO1 | O-3 | Opening | 24V Relay - S Valve
Clamp | CLI1 | I-3 | Opened | Clamp | CLO2 | O-4 | Closing | 24V Relay - S Valve
Clamp | CLI2 | I-4 | Closed | Hoist | HOO1 | O-5 | Lift Up | 24V Relay - Contactor
Hoist | HOI1 | I-5 | Up | Hoist | HOO2 | O-6 | Lowering | 24V Relay - Contactor
Hoist | HOI2 | I-6 | Up | Diverter | DVO1 | O-7 | To Blower | 24V Relay - S Valve
Hoist | HOI3 | I-7 | Down | Diverter | DVO2 | O-8 | To Vacuum | 24V Relay - S Valve
Hoist | HOI4 | I-8 | Down | Blower | BLO1 | O-9 | Blower On | 24V Relay - Contactor
Diverter | DVI1 | I-9 | Blowing | Vibrator | VBO1 | O-10 | Vibrator On | 24V Relay - Contactor
Diverter | DVI2 | I-10 | Vacuum | Tower Light | TWO1 | O-11 | Red Light | 24V Relay - Voltage
EMO | EMO | I-11 | EMO Relay | Tower Light | TWO2 | O-12 | Yellow Light | 24V Relay - Voltage
|  |  |  | Tower Light | TWO3 | O-13 | Green Light | 24V Relay - Voltage
Hoist Exceed Up Alarm | HAI1 | I-12
Hoist Exceed Down Alarm | HAI2 | I-13
No Bag Alarm | NBI1 | I-14